## DETALLES DEL PROYECTO
ID PROYECTO | 0
NOMBRE PROYECTO | FormaSER
PROJECT MANAGER
FECHA | 2024-04-08
VERSION | 1.0.0

## SPRINT 1
DAILY SCRUM
Miembro del equipo | Preguntas | Lunes | Martes | Miércoles | Jueves | Viernes | Sábado
Javier Andrés Serna Bañol | Qué se hizo ayer? |  | Desarrollod de Login, Register, y diagramas UML
| Qué se hará hoy? | Desarrollod de Login, Register, y diagramas UML | Casos de uso especifico, aplicativo para leer archivos excel y obtener sus datos
| Existe algún bloqueo para desarrollar la actividad? | Ninguno
Juan David Montoya | Qué se hizo ayer? |  | Busqueda y adaptación de plantilla para el diseño web
| Qué se hará hoy? | Busqueda y adaptación de plantilla para el diseño web | Diseño y maquetación de la página basdo en los requerimientos
| Existe algún bloqueo para desarrollar la actividad? | Ninguno
Jhon Alexander Narvadez Lopes | Qué se hizo ayer? |  | Diligenciación de formato de requerimientos eiii 830
| Qué se hará hoy? | Diligenciación de formato de requerimientos eiii 830 | tablas de casos de uso: Postcondiciones,Extensiones,Inclusiones,Prioridad
| Existe algún bloqueo para desarrollar la actividad? | Ninguno
[Name] | Qué se hizo ayer?
Qué se hará hoy?
Existe algún bloqueo para desarrollar la actividad?

## SPRINT 2
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?

## SPRINT 3
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?

## SPRINT 4
DAILY SCRUM TEMPLATE
Team member | Question | Monday | Tuesday | Wednesday | Thursday | Friday
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?